## 01_Risk_Criteria
CYBER RISK ASSESSMENT - RISK CRITERIA
LIKELIHOOD CRITERIA
Score | Rating | Definition
1 | Rare | Highly unlikely under current conditions
2 | Unlikely | Could occur, but limited exposure or strong controls exist
3 | Possible | Credible scenario with realistic conditions for occurence
4 | Likely | Expected to occur under existing conditions
5 | Almost Certain | Expected to occur frequently or imminently
IMPACT CRITERIA
Score | Rating | Definition
1 | Insignificant | Minimal operational or security impact
2 | Minor | Limited impact with minor service or security degradation
3 | Moderate | Noticeable operational, security, or business impact
4 | Major | Significant disruption, data exposure, or security impact
5 | Severe | Critical operational disruption, major data exposure, or severe business impact
RISK RATING CRITERIA
Score Range | Risk Level | Definition
1 -- 4 | Low | Acceptable risk; monitor through routine controls
5 -- 9 | Medium | Risk requires monitoring and appropriate mitigation
10 -- 16 | High | Significant risk requiring prioritized remediation
17 -- 25 | Critical | Unacceptable risk requiring immediate management attention
RISK MATRIX - LIKELIHOOD X IMPACT
Likelihood ↓ / Impact → | 1 Insignificant | 2 Minor | 3 Moderate | 4 Major | 5 Severe
Almost Certain (5) | 5 | 10 | 15 | 20 | 25
Likely (4) | 4 | 8 | 12 | 16 | 20
Possible (3) | 3 | 6 | 9 | 12 | 15
Unlikely (2) | 2 | 4 | 6 | 8 | 10
Rare (1) | 1 | 2 | 3 | 4 | 5

## 02_Risk_Register
CYBER RISK ASSESSMENT - RISK REGISTER
Risk ID | Asset | Threat | Vulnerability/ Condition | Existing Controls | Likelihood | Impact | Inherent Risk Score | Inherent Risk Level | Risk Treatment | Recommended Controls | Target Residual Likehood | Target Residual Impact | Target Residual Risk Score | Target Residual Risk Level | Risk Owner | Status | Assessment Rationale
RISK-001 | Check Point Security Gateway | Exploitation of vulnerabilities not covered by outdated IPS protections | IPS protection database could not be updated due to lack of Internet connectivity from the Security Gateway | IPS enabled; LAB-IPS-Detect profile active; Global Detect enabled; security policy deployed | 3 | 4 | 12 | High | Mitigate | Restore controlled Internet connectivity for IPS updates; update the IPS protection database; establish periodic update verification and monitoring | 2 | 4 | 8 | Medium | Network Security Team | Open | IPS protection updates were unavailable due to the gateway connectivity limitation. Exploitation is considered possible because outdated protections may reduce coverage against newer threats, while successful exploitation could cause significant security or operational impact
RISK-002 | LAB-LAN Test Endpoint | SQL Injection attack against na HTTP-accessible application or service | SQL Injection protection was configured as Drop + Log, but effective blocking could not be conclusively validated during testing | IPS enabled; LAB-IPS-Detect profile active; SQL Injection protection configured as Drop + Log; security policy deployed | 3 | 4 | 12 | High | Mitigate | Perform controlled SQL Injection testing; verify IPS Drop + Log enforcement; validate security logs and document blocking evidence. | 2 | 4 | 8 | Medium | Network Security Team | Open | SQL injection protection was configured as Drop + Log, but effective blocking was not conclusively demonstrated. The attack scenario remains credible until control effectiveness is validated, with potentially significant impact if explloitation succeeds
RISK-003 | LAB-LAN/ Windows 10 Endpoint | Unauthorized network communication from a compromised endpoint | Broad firewall access may permit more network communication than required by least-privilege principles | Check Point Acess Control policy; security logging; IPS and threat Prevention enabled | 2 | 3 | 6 | Medium | Mitigate | Review firewall rules using least-privillege principles; restrict unnecessary destinations and services; document business justification for broad access; perform periodic firewall rule reviews. | 1 | 3 | 3 | Low | Network Security Team | Open | Broad network access was intentionally permitted for laboratory testing. No endpoint compromise was observed, and preventive controls including IPS and Threat Prevention were enabled. However, equivalent broad access in a production environment could increase exposure to unauthorized network communication. Impact is rated Moderate because no critical data or production systems were demonstrated within the assessed LAB-LAN.
]

## 03_Asset_Register
CYBER RIKS ASSESSMENT - ASSET REGISTER
Asset ID | Asset Name | Asset Type | Business / Security Function | Environment | Confidentiality | Integrity | Availability | Overall Criticality | Asset Owner | Evidence Source | Notes
AST -001 | Check Point Gaia R82 Security Gateway | Security Infrastructure | Network access control, traffic enforcement, IPS and Threat Prevention | VirtualBox Security Lab | Medium | High | High | High | Network Security Team | Check Point R82 Lab - Technical Evidence | Primary security enforcement point used in the technical assessment
AST-002 | Windows 10 Test Endpoint | Endpoint | Traffic generation and security control validation | LAB-LAN | Low | Medium | Low | Medium | IT / Security Team | Check Point R82 Lab - Technical Evidence | Laboratory endpoint; no production or critical business data demonstrated
AST-003 | LAB-LAN | Network Segment | Isolated network for security testing and traffic validation | VirtualBox Security Lab | Low | Medium | Medium | Medium | Network Security Team | Lab Topology / Firewall Policy | Isolated laboratory network using 192.168.100.0/24
AST-004 | Check Point Mangement Enviroment | Security Management | Security policy administration and gateway management | Management Network | High | High | High | High | Security Administration Team | SmartConsole /Lab Architecture | Represents the management plane used for security policy administration
AST-005 | IPS Protection Database | Security Data / Protection Content | Provides current IPS protection signatures and security content | Check Point Threat Prevention | Low | High | High | High | Network Security Team | IPS Update Validation | Update failure was identified during technical validation
AST -006 | Check Point Security Policy | Security Configuration | Defines Access Control and Threat Prevention enforcement | Check Point R82 Lab | Medium | High | High | High | Network Security Team | SmartConsole/ Policy Installation Evidence | Includes Access Control and Threat Prevention configuration validated during the lab

## 04_Control_Register
CYBER RISK ASSESSMENT - CONTROL REGISTER
Control ID | Control Name | Control Domain | Control Objective | Related Asset(s) | Implementation Status | Control Effectiveness | Evidence ID | Evidence Description | Finding | Related Risk | Control Owner | Assessment Notes
CTRL-001 | Firewall Acess Control Policy | Network Security | Restrict network communications according to authorized security policy | AST-001;AST-002; AST-003; AST-006 | Implemented | Partially Effective | EV-001 | SmartConsole Access Control policy and successful policy installation evidence | Broad network access was intentionally permitted for laboratory testing and would require least-privilege review in a production environment | RISK-003 | Network Security Team | Control implementation was observed; production-equivalent rule design would require tighter destination and service restrictions
CTRL-002 | Intrusion Prevention System (IPS) | Threat Prevention | Detect and prevent network-based exploitation attempts | AST-001; AST-005; AST-006 | Implemented | Partially Effective | EV-002; EV-003 | IPS enabled and active; protection database update validation identified an update failure. | IPS protection database could not be updated. | RISK-001 | Network Security Team | IPS functionality was enabled, but protection currency could not be fully maintained under the observed connectivity condition.
CTRL-003 | SQL Injection IPS Protection | Application / Threat Prevention | Detect and block SQL Injection attack patterns in inspected HTTP traffic | AST-001; AST-002; AST-006 | Implemented | Not Conclusively Validated | EV-004 | SQL Injection protection configured as Drop + Log | Effective blocking could not be conclusively demonstrated during controlled testing. | RISK-002 | Network Security Team | Configuration evidence exists, but additional testing is required to establish operating effectiveness.
CTRL-004 | Security Event Logging | Security Monitoring | Generate security logs to support monitoring, investigation, and control validation. | AST-001; AST-004; AST-006 | Implemented | Effective | EV-005 | Logging was enabled within the assessed security policies and used during technical validation. | No material deficiency identified within the limited laboratory scope. | N/A | Network Security Team | Logging capability was observed within the laboratory scope; this assessment does not represent a full SIEM or SOC monitoring review.
CTRL-005 | Threat Prevention Policy | Threat Prevention | Apply configured threat prevention protections to relevant network traffic. | AST-001; AST-005; AST-006 | Implemented | Partially Effective | EV-006 | Threat Prevention profile was active and policy was successfully deployed. | Effectiveness is constrained by the IPS update finding and incomplete SQL Injection blocking validation. | RISK-001; RISK-002 | Network Security Team | Policy deployment was validated, while specific operating-effectiveness limitations remain documented separately.

## 05_Evidence_Register
CYBER RISK ASSESSMENT - EVIDENCE REGISTER
Evidence ID | Evidence Name | Evidence Type | Source | Related Asset(s) | Related Control(s) | Observation | Assessment Result | Related Risk | Evidence Status | Repository Reference | Notes
EV-001 | Access Control Policy Configuration | Screenshot / Configuration | Check Point SmartConsole | AST-001; AST-003; AST-006 | CTRL-001 | Access Control policy was configured and successfully installed on the Security Gateway | Control Implemented | RISK-003 | Validated | Check Point Lab Repository - Access Control evidence | Broad access was intentionally used for laboratory testing and is assessed separately under RISK-003
EV-002 | IPS Operational Status | CLI Output | Check Point Gaia CLI | AST-001; AST-005 | CTRL-002 | IPS was enabled and the LAB-IPS-Detect profile was active during validation. | Control Implemented | RISK-001 | Validated | Check Point Lab Repository - IPS status evidence | Technical evidence confirms IPS activation but does not by itself demonstrate protection currency.
EV-003 | IPS Protection Database update Validation | CLI Output / Technical Finding | Check Point Gaia CLI | AST-001; AST-005 | CTRL-002 | IPS protection database update could not be completed under the observed gateway connectivity condition. | Finding Identified | RISK-001 | Validated | Check Point Lab Repository - IPS update evidence | This evidence supports the protection-currency risk scenario documented as RISK-001
EV-004 | SQL injection Protection Configuration and Test | Configuration / Controlled Test | Check Point Smartconsole / LAB-LAN | AST-001; AST-002; AST-006 | CTRL-003 | SQL Injection protection was configured as Drop + Log; effective blocking was not conclusively demonstrated during testing. | Further Validation Required | RISK-002 | Validated with Limitation | Check Point Lab Repository — SQL Injection test evidence | Configuration evidence is available, but operating effectiveness remains inconclusive.
EV-005 | Security Logging Configuration | Screenshot / Configuration | Check Point Smartconsole | AST-001; AST-004; AST-006 | CTRL-004 | Logging was enabled within the assessed security policies | Control Implemented | N/A | Validated | Check Point Lab Repository - logging evidence | Evidence is limited to laboratory security logging and does not represent a full SIEM or SOC assessment.
EV-006 | Threat Prevention Policy Deployment | Screenshot / Configuration | Check Point SmartConsole | AST-001; AST-005; AST-006 | CTRL-005 | Threat Prevention profile was active and the policy was successfully deployed to the Security Gateway. | Control Implemmented with Limitations | RISK-001; RISK-002 | Validated | Check Point Lab Repository - Threat Prevention evidence | Control deployment was validated; specific effectiveness limitations are documented through EV-003 and EV-004.

## 06_Treatment_Plan
CYBER RISK ASSESSMENT - RISK TREATMENT PLAN
Action ID | RISK ID | Related Finding | Treatment Strategy | Remediation Action | Priority | Action Owner | Target Date | Status | Current Risk Level | Target Risk Level | Validation Method | Evidence Required | Management Notes
ACT-001 | RISK-001 | IPS protection database could not be updated due to lack of internet connectivity from the security gateway | Mitigate | Restore controlled internet connectivity for IPS updates; update the IPS protection database;establish periodic update verification and monitoring | High | Network Security Team | TBD | Open | High | Medium | Verify successful IPS protection database update and confirm protection currency through check point management and gateway validation | Sceenshot or CLI output showing successful IPS update status | Risk should be reassessed after remediation evidence is validated. Target residual risk is Medium and assumes IPS protection currency is restored and maintained
ACT-002 | RISK-002 | SQL Injection protection was configured as Drop + Log, but effective blocking could not be conclusively validated during testing | Mitigate | Perform controlled SQL injection testing; verify IPS Drop + Log enforcement; validate security logs and document blocking evidence | High | Network Security Team | TBD | Open | High | Medium | Execute controlled SQL Injection test traffic and verify that malicious requests are blocked and corresponding security events are logged | Test results, Smartconsole security logs, screenshots, and configuration evidence demonstarting SQL Injection blocking | Risk should be reassessed after effective blocking is demonstrated. Target risk is Medium assuming SQL Injection protection operates as intended
ACT-003 | RISK-003 | Broad firewall access was intentionally permitted for laboratory testing and requires least-privilege review before production-equivalent use | Mitigate | Review firewall rules using least-privilege principles; restrict unnecessary destinations and services; document business justification for required access | Medium | Network Security Team | TDB | Open | Medium | Low | Review the updated Access Control policy and verify that broad rules have been restricted to authorized sources, destinations, services, and required traffic flows | SmartConsole Access Control policy screenshot, rule review evidence, and documented justification for remaining permitted access | Laboratory access was intentionally broad for testing. Prpduction-equivalent deployment should apply least-privilege rules before the risk is considered reduced to Low

## 07_Executive_Summary
CYBER RISK ASSESSMENT - EXECUTIVE SUMMARY
ASSESSMENT OVERVIEW
Assessment : | Check Point Security Gateway Cyber Risk Assessment
Enviroment : | VirtualBox Cybersecurity Laboratory
Assessment Type : | Techical Cyber Risk anf Control Assessment
Primary Technology : | Check Point Security Gateway R82
Scope : | Access Control, IPS, Threat Prevention, Security Logging, Network Segmentation and Security Policy
Methodology : | Asset, threat, vulnerability, control and evidence-based risk assessment using a 5x5 likelihood-impact matrix
RISK OVERVIEW
Total Risks: | 3 | High: | 2 | Medium: | 1 | Critical: | 0
RISK REDUCTION OVERVIEW
Risk ID | Current Risk Score | Current Risk Level | Target Risk Score | Target Risk Level | Score Reduction
RISK-001 | 12 | High | 8 | Medium | 4
RISK-002 | 12 | High | 8 | Medium | 4
RISK-003 | 6 | Medium | 3 | Low | 3
KEY FINDINGS & MANAGEMENT CONCLUSION
KEY FINDINGS | Management Conclusion
The assessment identified three cybersecurity risk scenarios within the evaluated Check Point Security Gateway laboratory environment. Two risks were rated High and one was rated Medium. The primary risk drivers were the inability to maintain the IPS protection database under the observed connectivity conditions, incomplete validation of effective SQL Injection blocking, and broad network access permitted for laboratory testing. Existing security controls, including Access Control, IPS, Threat Prevention, and Security Logging, were implemented and operational; however, specific limitations reduced the level of assurance regarding their effectiveness. No Critical risks were identified during the assessment | The assessed environment demonstrates an established security control baseline; however, remediation is required to address the identified control limitations and reduce residual exposure. Priority should be given to restoring and validating IPS protection currency, conclusively validating SQL Injection prevention effectiveness, and reviewing network access rules according to least-privilege principles. Following implementation and validation of the recommended remediation actions, the assessed risk exposure is expected to decrease from two High and one Medium risks to two Medium and one Low risk. Residual risk should be formally reassessed after remediation evidence has been collected and validated.
.

## 08_Assessment_Signoff
CYBER RISK ASSESSMENT - ASSESSMENT SIGN-OFF
ASSESSMENT INFORMATION
Assessment : | Check Point Security Gateway Cyber Risk Assessment
Enviroment : | VirtualBox Cybersecurity Laboratory
Technology : | Check Point Security Gateway R82
Assessment Type: | Technical Cyber Risk and Controls Assessment
Assessment Status : | Completed
Assessment Date : | 2026-08-17
Assessor: | Enzo Marin
Version: | 1.0
ASSESSSMENT CONCLUSION
The cybersecurity risk assessment has been completed based on the defined scope, technical observations, control validation activities, and evidence collected during the assessment. Three cybersecurity risk scenarios were identified. Two were classified as High and one as Medium. No Critical risks were identified. Remediation actions have been defined for the identified risks. Target residual risk ratings represent the expected risk exposure following successful implementation and validation of the recommended controls and should not be interpreted as confirmed residual risk until remediation evidence has been reviewed.
FORMAL SIGN-OFF
Role | Name | Date | Approval/ Status
Assessor: | Enzo Marin | 2026-08-17 | Completed
Technical Reviewer: |  |  | Pending Review
Risk Owner: |  |  | Pending Acceptance
Management / Approver: |  |  | Pending Approval